Product Roadmap & Delivery Plan

Self-Hosted Campaign Management & Bulk Email Software

Document code: DOC-03
Version: 0.3
Date: 20 September 2026

Working title - replace with final product/client name during branding.

# 1. Delivery strategy

The project is divided into gated phases so the sending foundation is proven before higher-risk campaign volume is enabled. The target is an MVP that can be deployed, accepted and handed over cleanly rather than an indefinitely operated supplier-hosted service.

# 2. Indicative 10-week roadmap

| Week | Focus | Key outputs | Gate |
| --- | --- | --- | --- |
| 1 | Foundation | Repo, Docker, PostgreSQL, Redis, auth, RBAC, UI shell, CI/CD | User can securely access staging. |
| 2 | Foundation + data | Schema, migrations, settings, audit scaffolding | Core entities persist reliably. |
| 3 | Audience | Contacts, lists/tags, search, contact detail | Audience can be managed. |
| 4 | Imports + suppression | CSV import, mapping, dedupe, suppression checks | Large lists import safely. |
| 5 | Campaigns | Campaign setup, audience, templates, preview | Campaign draft is complete. |
| 6 | Rendering + tests | MJML, variables, test send, validation | Campaign can be rendered/tested. |
| 7 | Delivery engine | BullMQ workers, local SMTP submission, Postfix MTA, throttling, retries | Asynchronous direct-to-MX sending works. |
| 8 | Deliverability | Unsubscribe, bounces, complaints/feedback, DSNs, domains | Unsafe recipients are suppressed and delivery feedback is traceable. |
| 9 | Reporting | Campaign metrics, event history, exports | Operational results are visible. |
| 10 | Hardening + handover | Load/security tests, runbooks, training, deployment sign-off | Client accepts and takes control. |

# 3. Milestones

| Milestone | Definition of done |
| --- | --- |
| M1 - Staging ready | Authenticated application, database and queue services deployed to staging. |
| M2 - Audience ready | Contacts/lists/imports/suppression foundation accepted. |
| M3 - Campaign authoring ready | Campaign creation, template rendering, preview and test send accepted. |
| M4 - Sending engine ready | Queue workers, local SMTP submission, Postfix queue behavior, DNS identity and controlled external delivery validated. |
| M5 - Compliance controls ready | Unsubscribe, bounce and complaint processing validated end-to-end. |
| M6 - Production handover | Load test, backups/runbook, credentials and acceptance package completed. |

# 4. Dependencies

Client cloud/server account and deployment access.

Client-owned domain/subdomain and ability to edit DNS.

Static sending IP, outbound TCP/25 approval, PTR/rDNS control and sending-domain DNS access.

Bounce/DSN ingestion path and complaint-feedback ingestion where mailbox providers make it available.

Brand assets and default email footer/business information.

Client nominees for administrator and acceptance testing.

Agreed retention/backups policy and target recovery expectations.

# 5. Release gates

No production send before PTR/rDNS, SPF, DKIM, DMARC, HELO identity and direct-to-MX connectivity checks pass.

No broad campaign before suppression/unsubscribe controls pass integration tests.

No handover before backup/restore and worker restart procedures are documented.

No acceptance before privileged credentials and ownership boundaries are confirmed.

# 6. Post-MVP options

Advanced segmentation and behavioral filters.

A/B testing for subject/content variants.

Automated email sequences and event-triggered workflows.

Organization-level multi-tenancy if the product later becomes centralized SaaS.

Optional relay adapters, advanced domain/IP reputation dashboards and custom analytics.

Optional support/maintenance releases under a separate agreement.