Project Cost Estimate & Budget Model

Self-Hosted Campaign Management & Bulk Email Software

Document code: DOC-09
Version: 0.3
Date: 20 September 2026

Working title - replace with final product/client name during branding.

# 1. Purpose and estimate basis

This document provides an initial planning budget for the MVP defined in DOC-02 and the related technical/UX documents. It separates the one-time build/deploy/handover cost from the recurring services the client will pay directly after handover. It is a budget model, not a binding quotation.

Pricing status All figures are planning estimates in USD and should be replaced with the supplier's approved rates and current hosting/IP/monitoring quotations before a commercial proposal is issued. Live vendor pricing has not been verified in this documentation update.

# 2. Executive cost summary

| Cost category | Planning basis | Estimated amount | Paid by |
| --- | --- | --- | --- |
| MVP engineering effort | Approx. 400-580 delivery hours | Depends on supplier rate | Client -> Supplier |
| Illustrative build cost @ $35/hour | 400-580 hours | $14,000-$20,300 | Client -> Supplier |
| Illustrative build cost @ $50/hour | 400-580 hours | $20,000-$29,000 | Client -> Supplier |
| Illustrative build cost @ $75/hour | 400-580 hours | $30,000-$43,500 | Client -> Supplier |
| Illustrative fixed-price envelope | ~$50/hour basis + contingency | $24,000-$35,000 | Client -> Supplier |
| Client recurring infrastructure | Hosting, backup, static IP, monitoring, optional relay | Approx. $40-$520+/month | Client -> Vendors |

The fixed-price envelope is an illustrative budgeting range, not a recommended margin or final client quote. The supplier should price the engagement based on its actual blended delivery rate, tax position, staffing model, warranty/support commitments and commercial risk.

# 3. Estimated implementation effort

| Workstream | Low hours | High hours | Includes |
| --- | --- | --- | --- |
| Discovery & architecture | 24 | 40 | Requirements refinement, architecture, data model, delivery planning |
| UX & application shell | 32 | 48 | Navigation, core screens, responsive layout, reusable components |
| Authentication & administration | 24 | 36 | Login, roles, users, system/MTA settings |
| Audience & imports | 48 | 64 | Contacts, lists, tags, CSV import, validation, deduplication |
| Campaigns & templates | 56 | 80 | Campaign wizard, templates, personalization, preview/test send |
| Queue & sending integration | 64 | 96 | Redis/BullMQ, workers, Postfix integration, DSN processing, rate limiting |
| Deliverability controls | 48 | 72 | Suppression, unsubscribe, DSN/bounce/complaint feedback, DNS identity checks |
| Reporting & audit history | 32 | 48 | Campaign metrics, events, exports/audit views |
| Testing & production hardening | 40 | 56 | Functional/integration tests, security checks, load testing |
| Deployment & handover | 32 | 40 | Client environment deployment, runbooks, training, acceptance |
| TOTAL | 400 | 580 | Estimated MVP engineering effort |

# 4. Rate-based build-cost scenarios

| Blended supplier rate | Low (400 h) | High (580 h) | Use case |
| --- | --- | --- | --- |
| $35/hour | $14,000 | $20,300 | Lean/low-cost delivery benchmark |
| $50/hour | $20,000 | $29,000 | Mid-range planning benchmark used in this pack |
| $75/hour | $30,000 | $43,500 | Senior/specialist delivery benchmark |
| $100/hour | $40,000 | $58,000 | Higher-cost consultancy benchmark |

For a fixed-price project, the supplier may add contingency for requirement uncertainty, rework, project management, warranty obligations and commercial risk. Change requests should be quoted separately under the change-control process in DOC-00 and DOC-02.

# 5. Client-owned recurring operating costs

Because the system is deployed and handed over into client-controlled infrastructure, these costs are normally paid directly by the client to the selected vendors rather than passed through the supplier.

| Item | Typical planning range | Billing cycle | Notes |
| --- | --- | --- | --- |
| Domain name | $10-$30 | Per year | Existing client domain may be used; separate marketing subdomain usually does not require another domain purchase. |
| Application/server hosting | $30-$100 | Per month | Typical starting range for a modest VPS/cloud deployment; topology can be split as load grows. |
| Backups/snapshots | $5-$30 | Per month | Depends on retention, database size and provider. |
| Object storage/log retention | $5-$40 | Per month | Optional/usage-based; for assets, exports and retained logs. |
| Monitoring | $0-$50 | Per month | Open-source tooling can be self-hosted; managed monitoring costs extra. |
| Outbound MTA/deliverability operations | $0-$200+ | Per month | No mandatory per-message relay fee for direct-to-MX; allowance covers optional monitoring, extra IPs/tools or contingency relay. Current vendor pricing not verified. |
| Static/dedicated sending IP + deliverability tooling | $0-$100+ | Per month | Infrastructure-dependent; confirm public IPv4/rDNS and monitoring pricing before purchase. |
| TLS certificate | $0 | Per year | Can use Let's Encrypt where appropriate. |
| Core application stack licenses | $0 | Ongoing | Planned stack is based primarily on open-source components. |

Indicative recurring budget is now dominated by VPS/static-IP, backups and optional monitoring/contingency relay rather than per-message email-provider fees. Confirm current vendor pricing before approval.

# 6. One-time external/client costs

Initial domain purchase if the client does not already own an appropriate domain.

Any paid hosting/network onboarding, additional public IPs, deliverability monitoring or optional fallback SMTP relay selected by the client.

Cloud/server deposits or prepaid credits where required by the selected infrastructure provider.

Independent legal/compliance review requested by the client.

Optional commercial email-template builder or third-party validation service if the client chooses tools outside the open-source baseline.

# 7. Optional post-handover support budget

Ongoing support is not part of the default build-deploy-handover engagement. If offered, it should be contracted separately. The following are placeholders for commercial planning only:

| Support model | Illustrative range | Typical coverage |
| --- | --- | --- |
| Ad-hoc support | $50-$100/hour | Bug investigation, configuration help, minor changes; billed as used. |
| Maintenance retainer | $300-$1,000/month | Limited support hours, dependency/security updates, periodic health review. |
| Enhanced support | $1,000-$2,500+/month | Faster response targets, more included hours, proactive maintenance; scope must be defined. |

# 8. Suggested commercial payment milestones

| Milestone | Suggested share | Trigger |
| --- | --- | --- |
| Project kickoff | 30% | Contract/SOW signed and project starts |
| Foundation & UX baseline | 25% | Core architecture, auth, app shell and approved wireframes available |
| Feature-complete staging | 25% | MVP feature set deployed to staging and integration testing underway |
| Acceptance & handover | 20% | Acceptance criteria passed and handover package delivered |

Payment milestones are a commercial template only and should be reconciled with the supplier's standard contract, taxes and client procurement requirements.

# 9. Cost responsibility matrix

| Cost / obligation | Supplier | Client |
| --- | --- | --- |
| Software design/build effort | Included in project fee | Pays agreed project fee |
| Deployment labor | Included if within agreed scope | Provides environment/access |
| Cloud/VPS hosting | No recurring obligation after handover | Owns and pays hosting/network provider |
| Domain/DNS | Configures as scoped | Owns and pays DNS/domain provider |
| Outbound MTA | Implements and hands over client-controlled MTA | Owns/operates sending IP, DNS and reputation |
| Production recipient data | Does not supply list | Owns and is responsible for data/use |
| Post-handover operations | Not included by default | Operates and monitors system |
| Support/maintenance | Only if separately contracted | Optional purchase |

# 10. Quote exclusions and cost risks

Hosting, monitoring or optional relay price changes, currency movements, taxes and usage overages.

Major scope additions such as multi-tenancy, billing/subscriptions, multi-region/shared MTA infrastructure, advanced automation, CRM or multichannel messaging.

Unplanned migrations from unsupported legacy systems or large-scale data cleansing.

Extended warranty/support beyond the period stated in the commercial agreement.

Legal services, regulatory filings or deliverability guarantees.

Costs caused by client abuse, hosting/network suspension, blocklist/reputation remediation or replacement infrastructure after handover.

# 11. Budget decision before contract signature

Before issuing the final proposal, replace the planning numbers in this document with the supplier's approved hourly/blended rate or fixed project price, confirm the client-selected infrastructure, static-IP and monitoring costs, obtain current vendor quotations, state applicable taxes, and attach the resulting commercial schedule to the signed agreement.